## Sheet1
REQUEST NO.	REQUESTOR	REQUEST DATE	REQUEST	REQUEST JUSTIFICATION	RESOLUTION/NOTES
1	Kepper	2009-07-31	@type on graphic		Add @type on surface and zone instead, restricting graphic to use of @internetmedia? Use @n instead of adding @type?
2	Kepper	2009-07-31	add "within" in data.PLACE		Conflicts with data.PLACE usage in clef.dis
3	Roland	2009-07-31	add sameAs, copyOf, etc. attributes		Added copyof, sameas, and synch attribute to att.common.anl in 19b.1/RNG 9/17/09
4	Roland	2009-07-31	put att.link.common and href attributes in xlink namespace		Added to 19b.1/RNG 10/21/09
5	Roland	2009-07-31	put ID attribute in xml namespace		Added to 19b.1/RNG 9/17/09
6	?	2009-07-31	add @synch on when in order to point from when back into transcription		“synch” is not the proper name here. See #3. Used “data” instead, similar to @data on source.
7	?	2009-07-31	create “non-sung text” element in order to accommodate spoken dialog		use MEI <anchoredtext>, <dir>, or elements from model.textcomponentLike?
8	?	2009-07-31	add @type on tie/slur		Added to 19b.1/RNG 9/17/09
9	Sapp	2009-08-11	add join (?) attribute on measure for indicating another measure that metrically completes the current one		Added to 19b.1/RNG 9/17/09
10	Sapp	2009-08-11	change "15va" to "15ma" in @clef.trans		no longer necessary; see #13
11	Sapp	2009-08-11	add "15mb" ("quindicesima bassa") in @clef.trans		no longer necessary; see #13
12	Sapp	2009-07-31	provide for multiple expan lists		Added to Modularized/shared_Module.rng 01/15/2010
13	Roland	2009-08-17	replace @clef.trans (and similar places) with @dis and @dis.place		Added to 19b.1/RNG 9/17/09
14	Roland	2009-08-24	@numbase datatype = positiveInteger not duration		Added to 19b.1/RNG 9/17/09
15	Roland	2009-08-25	add lem element to app		Added to 19b.1/RNG 9/18/09
16	Roland	2009-09-02	revise instrdef handling, see instrdefRevisionExample.mei		Added to 19b.1/RNG 9/17/09
17	Roland	2009-09-03	restrict midi.instrname to Gen. MIDI list		Added to 19b.1/RNG 9/17/09
18	Viglianti	2009-09-07	app in fw, pgheadN, pgfootN		Added to Modularized/shared_Module.rng 01/15/2010
19	Viglianti	2009-09-07	app in tuplet (beam too?)		Added to cmn_Module.rng 03/24/2010
20	Siegert	2010-02-12	value “unknown” for @grace	Sometimes it's not possible to know a priori if a grace note is accented or unaccented.	Added to datatypes.rng 03/24/2010
21	Kepper	2010-03-04	allow controlevent-like attributes (@staff, @tstamp, etc.) on artic	See JK's emails.
22	Roland	2010-03-04	2mei should create tie elements in addition to/rather than @tie attributes; 2mup should convert tie elements to Mup curve statements.	Better visual rendition. However, better visual rendition comes at the cost of less satisfactory automatic performance	Added to 2mei-2.2.3.xml 04/28/2010
23	Kepper	2010-03-04	create history element containing a list of events. Model after EAD chronlist?	See JK's emails.	Added to header_Module.rng 03/24/2010
24	Selfridge-Field	2010-03-04	frame entity (which is just an empty block of text space) would be great for accommodating stage instructions and some of kinky bits that turn up in unedited material.		use MEI <anchoredtext>, <dir>, or elements from model.textcomponentLike
Requests to be handled in MEI ODD
25	Roland	2010-10-04	add <relateditem> to <source>; modify schematron to allow @source to point to <source> or <relateditem>	Need to describe constituent intellectual parts of a bibliographic source or alternative versions	Added relateditem 2010-12-10; schematron now allows any element w/ @decls (see # 28) to point to any element within meihead
26	Roland	2010-10-04	rename <accessdesc> to <accessrestrict>	Better if name parallels <userestrict>	Changed name 2010-12-10
27	Roland	2010-10-04	permit <scoredef> directly within <part>	<part> is a kind of score	Added 2010-12-10
28	Roland	2010-10-04	add att.declaring class containing decls attribute (IDREF or URI?); members: music, mdiv, section, part, staff, layer, measure, back, body, div, facsimile, front, group, lg, p, surface, performance, recording, clip; remove facsimile from att.source.attributes class; add sch:rule to check that @decls references a member of declarable class, that is, availability, correction, editorialdecl, interpretation, langusage, normalization, projectdesc, samplingdecl, segmentation, source, stdvals; remove att.datapointing class?	Need reference to metadata for encoding of composite encodings, such as a collection of songs; att.datapointing class encourages forward references	Added 2011-01-13; left att.datapointing in place; schematron now allows any element w/ @decls to point to any element within meihead; added availability, classification, correction, editorialdecl, interpretation, langusage, normalization, projectdesc, samplingdecl, segmentation, stdvals to att.datapointing class
29	Roland	2010-10-04	allow mods:mods as replacement for/content of mei:filedesc, mei:sourcedesc, mei:workdesc, mei:relateditem
30	Roland	2010-10-04	add @authority to <reg>	Useful for documenting source of authorized, regularized forms	2011-01-13 added @reg to att.authority; made <reg> member of att.authority
31	Roland	2010-10-04	rename <date>/@reg to @regdate	“reg” (where the thing being regularized is the date) is confusing on names	Cancel – better addressed by removing reg from att.datable and adding reg directly to date
32	Roland	2010-10-04	fix typos in <list> documentation: “as” = “a”, “of” = “or”		Fixed 2011-01-13
33	Roland	2010-10-04	resolve problems with mei ns in schematron		Resolved by changes to Roma and by adding sch:ns elements to schematron rules (RV)
34	Roland	2010-10-04	rewrite documentation for <classcode>	Improved documentation. Benni?	2011-01-13
35	Roland	2010-10-04	allow att.link.external on <classcode>; make classcode EMPTY	use to point to electronic version of the classification system; discourage use of classcode to hold values	2011-01-13 added classcode to att.authorized and modified its content model to be more restrictive, but not EMPTY
36	Roland	2010-10-04	fix sch:rule for @classcode – preceding axis not appropriate	@classcode may not always follow classcode element it references	2011-01-13
37	Roland	2010-10-04	TEI @ref != MEI @analog. Is MEI att.bibl = TEI att.canonical? Create MEI att.canonical? Add @analogURI to MEI's att.bibl?	resolve confusion between @authority, @dbkey, @analog	removed dbkey from att.name; created att.canonical (@dbkey [nmtoken]); made members of att.name also members of att.canonical and att.authorized (authority, authURI, reg); analogURI NOT added, use authURI where available
38	Roland	2010-10-04	allow <creation> to be empty? Use zeroOrMore content model?	empty creation element useful during file creation	Cancel – already possible
39	Roland	2010-10-04	Create documentation for MEI classes: att.internetmedia, att.sequence, att.staffident, att.startid, att.layerdef.vis, attlchord.ges.cmn, att.chord.log.cmn, att.space.log.cmn, att.reasonident, att.declaring, att.facsimile, model.controleventLike, model.scoredefLike, model.staffPart, model.startLike.header, model.eventLike.mensural, model.eventLike.neumes, model.layerPart.neumes, model.startLike.corpus, model.facsimileLike, model.figureLike, model.graphicLike, model.figdescLike, model.rdgPart.text	Improve documentation	Added 2010-01-19
40	Roland	2010-10-05	remove reference to musicchar.ent in musicxml2mei.xsl	Not currently used for transformation; when this .ent file isn't available, it causes the transformation to fail
41	Roland	2010-10-12	allow <timeline> in <music>	permits timeline declaration higher up in the document hierarchy	2011-01-13 added model.alignLike and new model.performanceLike class to <music>; on timeline: removed medialength and unit (att.measurement); substituted avref for mediacontent
42	Roland	2010-10-12	add sch:rule to require @absolute or @since on <when>		IGNORE! Too restrictive during document creation process
43	Roland	2010-10-12	on <when> – change datatype of @absolute to data.ISOTIME, change datatype of @interval to text, remove att.measurement, add inttype with values: byte, smil, midi, smpte-25, smpte-24, smpte-df30, smpte-ndf30, smpte-df29.97, smpte-ndf29.97, tcf, time		2011-01-13 required use of data.ISOTIME for @absolute; removed att.measurement; loosened requirement for @interval; added @inttype
44	Roland/Kepper	2010-11-19	use anyURI instead of IDREF	permits “outside” as well as “inside” references	tabled – addition of @authURI or @href sufficient?
45	Roland	2010-11-19	add <recording> as sibling of <facsimile>?	handle audio reproductions in a manner similar to graphic reproductions (facsimiles)	2011-01-13 added performance module (analogous to facsimile module) with elements performance, recording, clip, and avfile
46	Hartwig/Kepper	2010-11-19	harm/figured bass revision	proposal for figured bass posted on MEI-L 2010-11-15	Added 2011-01-27
47	Roland	2010-12-06	fix all occurrences of the definition of interline distance - “half the distance between adjacent staff lines”	not clearly defined everywhere	Fixed 2011-01-19
48	Roland	2010-12-06	remove entityref from att.link.external	preparation for anyURI
49	Roland	2010-12-06	remove reg from att.datable; add directly to <date>	prevents confusion when att.datable is added to nameLike elements	Removed @reg from att.datable; added it directly to date element and att.authorized class
50	Roland	2010-12-06	document each attDef with <desc>	Improved documentation	Added 2010-12-10
51	Roland	2010-12-06	correct omission of width attr on graphic		2011-01-13 added graphic to att.width class
52	Roland	2010-12-06	edit att.calendared <desc>	Improved documentation	Revised 2011-01-13
53	Roland	2010-12-06	force classcode to be empty		IGNORE! See #35
54	Roland	2010-12-06	add att.staffident to att.tupletspan.log		2011-01-13 made att.tupletspan.log member of att.controlevent which provides att.staffident
55	Roland	2010-12-06	since model.metLike.score_sequenceOptional seems to require elements be declared in order, re-order pghead1, pghead2, pgfoot1, pgfoot2 in mei-source		Added 01/13/2011
56	Roland	2010-12-14	restrict @pos on chorddef to positiveInteger		Added 2011-01-13
57	Roland	2010-12-14	allow @staff to have multiple values		Added 2011-01-13
58	Roland	2010-12-14	revise parameters for tab.strings and key.sig.mixed to allow a wider range of articulation signs		Added 2011-01-27
59	Roland	2010-12-14	add att.internetmediatype to extref		2011-01-13 Added att.internetmediatype to extref and extptr
60	Roland	2010-12-15	fix definition of data.COLOR	choice unnecessary	Fixed 2011-01-13
61	Roland	2010-12-15	add constraint for lines.color	either a single value of same # of values as lines	Currently in mei2011-05-modification.xml
62	Roland	2010-12-15	tab.strings token, not NMTOKEN	'#' not permitted in NMTOKENs	Added 2011-01-27
63	Roland	2010-12-15	add model classes for relateditem, performance (and children), figured bass elements		Added model.performanceLike 01/13/2011; added model.figbassLike 2011-01-27
64	Roland	2010-12-15	add graphicprimitiveLike and fLike to elements in transcriptionLike class		Added 2011-01-27
65	Roland	2010-12-15	replace 'slash' in data.textrendition with 'bslash' (back slash) and 'fslash' (forward slash)		Added 01/13/2011
66	Roland	2010-12-15	add 'all' as value for @staff?	perhaps 'every' is a better choice of term, the idea being to say with a single word the fact that each staff / all staves is/are indicated	Tabled – not explicit enough?
67	Roland	2010-12-15	rename <keywords> to <termlist> and add @classcode	improve usability; groups of terms may be associated with a class code	Added 01/13/2011
68	Roland	2010-12-15	add watermark and plate to physdesc	syntactic sugar for physmedium, but common enough to warrant use	Added 01/13/2011
69	Roland	2010-12-15	@staff “mandatory when applicable”	allow @staff NOT to be specified when using MEI elements within TEI	Added 01/13/2011
70	Dabbert	2010-12-15	add @complete on staff and layer?	granularity below the measure level is needed	Currently in mei2011-05-modification.xml
71	Roland for Axel	2010-12-15	add relateditem to <filedesc> and <profiledesc>?		No longer necessary after introduction of workdesc and the addition of relateditem to source and work
72	Roland	2010-12-15	add head to eventlist, using list as a model		Added 01/13/2011
73	Roland	2011-01-28	add att.bibl class to annot	need method to indicate mapping of individual annotations to other bibliographic standards	Currently in mei2011-05-modification.xml
74	Roland	2011-03-29	document attr value lists using valItem/desc	Improved documentation	Added 03/29/2011
75	Roland	2011-03-30	add <lg> to content of <lg>		Currently in mei2011-05-modification.xml
76	Roland	2011-03-30	add workdesc directly within header; replaces profiledesc	permits description of work without having to describe sources of the work	Currently in mei2011-05-modification.xml
77	Roland	2011-04-04	add att.edit and att.trans classes to subst	more closely imitates TEI, treats subst like other members of these classes, allows capture of this info about the subst and not just its sub-elements	Currently in mei2011-05-modification.xml
78	Viglianti	2011-04-04	add att.duration.timestamp to att.log.tie	will allow @dur (i.e., ending tstamp) on tie	Currently in mei2011-05-modification.xml
79	Roland	2011-04-05	allow music content in abbr and expan as in other editorial elements, such as sic, corr, etc.		use same model as sic, etc. but drop sectionLike, measureLike, staffLike, layerLike?
80	Kepper	2011-04-01	creating pointing mechanism from zone (also surface and facsimile?) to transcriptional “data”		use @data. Currently in mei2011-05-modification.xml
81	Roland	2011-04-05	revise 2mei and 2mup stylesheets	account for changes in schema between 2010-05 and 2011-05 releases
82	Roland	2011-04-05	Create 2010-05 to 2011-05 xslt conversion?
83	Hankinson	2011-04-26	document origin as upper left corner in surface	make origin explicit	Added in mei-2011-05-source.xml 4/26/2011
84	Viglianti	2011-04-03	account for “in-staff” ossia		revisions to handling of measure and staff ossias currently in mei2011-05-modification.xml